## Total Project Tracking
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Screen | Customer | Guest, Customer |  | Tiến | Done | iter1 | iter1
2 | Category Screen | Product | Guest, Customer |  | An | Done | iter1 | iter1
3 | Product Details | Product Details | Guest, Customer |  | An | Done | iter1 | iter1
4 | Login Screen | Customer | Guest, Customer |  | Tiến | Done | iter1 | iter1
5 | News Screen | Customer | Guest, Customer |  | Tiến | Done | iter1 | iter1
6 | Database | System |  | Create Database for project | Phúc | Done | iter1 | iter1
7 | Admin Login Screen | Admin | Admin | Login for admin account | Quân | Done | iter1 | iter1
8 | DAO | System |  |  | Phúc | Done | iter1 | iter1
9 | Header-Footer loaded from db | Customer | Guest, Customer |  | Tiến | Done | iter1 | iter1
10 | Add new news | News | Manager, Admin |  | Tiến | Done | iter1 | iter1
11 | Cart | Shopping | Customer |  | An | Done | iter2 | iter2
12 | User Details | User | Admin, Manager, Customer |  | Tiến | Done | iter2 | iter2
13 | Product List | Management | Manager, Admin |  | An | Done | iter2 | iter2
14 | Product Details | Management | Manager, Admin |  | An | Done | iter2 | iter2
15 | News Detail | Management | Manager, Admin |  | Tiến | Done | iter2 | iter2
16 | Product Rate | Rate | Customer |  | An | Done | iter2 | iter2
17 | Contact Screen | Customer | Guest, Customer |  | Tiến | Done | iter2 | iter2
18 | Login Verification | Validation |  |  | Quân | Done | iter2 | iter2
19 | Send Email | Message |  |  | Phúc | Done | iter2 | iter2
20 | Customer List | Management | Manager, Admin |  | Tiến | Done | iter2 | iter2
21 | Edit news | News | Manager, Admin |  | Tiến | Done | iter2 | iter2
22 | FAQ Screen | Customer | Guest, Customer |  | Tiến | Done | iter3 | iter3
23 | Checkout | Shopping | Customer |  | An | Done | iter3 | iter3
24 | Dashboard | Management | Manager, Admin |  | An | Done | iter3 | iter3
25 | Order List | Order | Manager, Admin |  | An | Done | iter3 | iter3
26 | Order Details | Order | Customer |  | An | Done | iter3 | iter3
27 | News Notification | Management | Manager, Admin |  | Tiến | Done | iter3 | iter3
28 | Statistics | Management | Manager, Admin |  | Nhật | Done | iter3 | iter3
29 | Manager List | Management | Admin |  | Tiến | Done | iter3 | iter3
30 | Voucher List | Management | Manager, Admin |  | Tiến | Done | iter3 | iter3
31
32
33
34
35
36
37
38
39
40
31 | Discount List | Management | Manager, Admin |  | An | Done | iter3 | iter3
32 | Warranty | Management | Manager, Admin |  | Tiến | Done | iter3 | iter3
33 | Banner | Management | Manager, Admin |  | Tiến | Done | iter3 | iter3
34 | Service Tag | Management | Manager, Admin |  | An | Done | iter3 | iter3

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Screen | Public |  | Phúc | Done
2 | Category Screen | Public |  | An | Done
3 | Product Details | Public |  | Nhật | Done
4 | Login Screen | Public |  | Quân | Done
5 | News Screen | Public |  | Tiến | Done
6 | Database | System | Create Database and add data for project | Phúc | Done
7 | Admin Login Screen | Admin | Login for admin account | Quân | Done
8 | DAO | System |  | Phúc | Done
9 | Header-Footer loaded from db | Public |  | Tiến | Done
10
11
12
13
14
15
16
17
18
19
20

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
3 | Product List | Management |  | An | Done
4 | Product Details | Management |  | An | Done
6 | Product Rate | Rate |  | Nhật | Done
1 | Cart | Shopping |  | Phúc | Done
9 | Send Email | Message |  | Phúc | Done
10 | Customer List | Management |  | Phúc | Done
2 | User Details | User |  | Quân | Done
8 | Login Verification | Validation |  | Quân | Done
5 | News Detail | Management |  | Tiến | Done
7 | Contact Screen | Customer |  | Tiến | Done
11 | Edit news | News |  | Tiến | Done
12
13
14
15
16
17
18
19
20

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | FAQ Screen | Customer |  | Tiến | Done
2 | Checkout | Shopping |  | Phúc | Done
3 | Dashboard | Management |  | Phúc | Done
4 | Order List | Order |  | Quân | Done
5 | Order Details | Order |  | Quân | Done
6 | News Notification | Management |  | Tiến | Done
7 | Statistics | Management |  | Nhật | Done
8 | Manager List | Management |  | Phúc | Done
9 | Voucher List | Management |  | Phúc | Done
10 | Discount List | Management |  | An | Done
11 | Warranty | Management |  | Quân | Done
12 | Banner | Management |  | Tiến | Done
13 | Order Details | Management |  | An | Done
14
15
16
17
18
19
20

## Iter4
Iteration Tracking - Iteration 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Screen | Public |  | Phúc | To Do | II.3 | III.5
2 | Category Screen | Public |  | An | To Do | II.1 | III.4
3 | Product Details | Public |  | Nhật | To Do | II.2 | III.5
4 | Login Screen | Public |  | Quân | To Do | II.3 | III.6
5 | News Screen | Public |  | Tiến | To Do | II.4 | III.7
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20